## Gantt Chart
PROJECT GANTT CHART
Project timeline: 01 September 2026 – 2027-07-30
PROJECT START |  | PROJECT FINISH |  | ACTIVITIES |  | PHASES
2026-09-01 |  | 2027-07-30 |  | 42 |  | 6
[7 empty] | SEP 2026 |  |  |  |  | OCT 2026 |  |  |  |  | NOV 2026 | [5 empty] | DEC 2026 |  |  |  |  | JAN 2027 |  |  |  |  | FEB 2027 |  |  |  | MAR 2027 |  |  |  |  | APR 2027 |  |  |  |  | MAY 2027 | [5 empty] | JUN 2027 |  |  |  |  | JUL 2027
ACTIVITY | ACTIVITY NAME | PHASE | START | FINISH | DAYS | PREDECESSOR | 1 | 7 | 14 | 21 | 28 |  | 5 | 12 | 19 | 26 |  | 2 | 9 | 16 | 23 | 30 |  | 7 | 14 | 21 | 28 |  | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 1 | 8 | 15 | 22 | 29 |  | 5 | 12 | 19 | 26 |  | 3 | 10 | 17 | 24 | 31 |  | 7 | 14 | 21 | 28 |  | 5 | 12 | 19 | 26
2.0 | Design and legal validation of consent mechanism and privacy notice | Phase 2 | 2026-09-01 | 2026-09-15 | 11 | -
2.1a | Decision on identification method | Phase 2 | 2026-09-01 | 2026-09-01 | 1 | -
2.1b | Visual design of the chosen system | Phase 2 | 2026-09-02 | 2026-09-08 | 5 | 2.1a
2.2a | Technical audit of POS terminal | Phase 2 | 2026-09-01 | 2026-09-03 | 3 | -
2.2a-bis | Deep technical exploration of POS API | Phase 2 | 2026-09-04 | 2026-09-21 | 12 | 2.2a
2.2b | Development of POS integration connector | Phase 2 | 2026-09-22 | 2026-10-05 | 10 | 2.2a-bis
2.2c | Testing of invoice to card linkage | Phase 2 | 2026-10-06 | 2026-10-12 | 5 | 2.2b
2.3a | Dashboard mockup and data architecture design | Phase 2 | 2026-10-06 | 2026-10-09 | 4 | 2.2b
2.3b | Development of dashboard interface and data connection | Phase 2 | 2026-10-12 | 2026-10-21 | 8 | 2.3a
2.4 | Internal testing before pilot deployment | Phase 2 | 2026-10-22 | 2026-10-30 | 7 | 2.2c,2.3b,2.1b
3.1a | Basic analysis of purchase patterns | Phase 3 | 2026-09-01 | 2026-09-04 | 4 | -
3.1b | Definition of incentive mechanism | Phase 3 | 2026-09-07 | 2026-09-08 | 2 | 3.1a
3.2a | Design of communication materials | Phase 3 | 2026-09-09 | 2026-09-10 | 2 | 3.1b
3.2b | Review and validation cycle | Phase 3 | 2026-09-11 | 2026-09-14 | 2 | 3.2a
3.2c | Printing and installation | Phase 3 | 2026-09-15 | 2026-09-21 | 5 | 3.2b
3.3 | Development of training script for checkout staff | Phase 3 | 2026-09-09 | 2026-09-11 | 3 | 3.1b
4.1 | Activation of data logging | Phase 4 | 2026-11-02 | 2026-11-03 | 2 | 2.4
4.wait1 | Data accumulation period before first checkpoint | Phase 4 | 2026-11-04 | 2026-12-01 | 20 | 4.1
4.2a | First data quality checkpoint | Phase 4 | 2026-12-02 | 2026-12-03 | 2 | 4.wait1
4.wait2 | Data accumulation period before second checkpoint | Phase 4 | 2026-12-04 | 2026-12-31 | 20 | 4.2a
4.2b | Second data quality checkpoint | Phase 4 | 2027-01-01 | 2027-01-04 | 2 | 4.wait2
4.wait3 | Data accumulation period before final validation | Phase 4 | 2027-01-05 | 2027-02-01 | 20 | 4.2b
4.2c | Final data quality validation (3 months of data) | Phase 4 | 2027-02-02 | 2027-02-03 | 2 | 4.wait3
5.1 | Distribution of loyalty cards | Phase 5 | 2026-11-02 | 2026-11-04 | 3 | 2.4,3.2c,2.0
5.2 | Training delivery and observation tour | Phase 5 | 2026-11-05 | 2026-11-10 | 4 | 3.3,5.1
5.3 | Launch of discount voucher campaign | Phase 5 | 2026-11-11 | 2026-11-12 | 2 | 5.2
5.wait1 | Adoption ramp-up period before first checkpoint | Phase 5 | 2026-11-13 | 2027-01-07 | 40 | 5.3
5.4a | First adoption checkpoint | Phase 5 | 2027-01-08 | 2027-01-11 | 2 | 5.wait1
5.wait2 | Adoption ramp-up period before mid checkpoint | Phase 5 | 2027-01-12 | 2027-04-05 | 60 | 5.4a
5.4b | Mid campaign adoption checkpoint | Phase 5 | 2027-04-06 | 2027-04-07 | 2 | 5.wait2
5.wait3 | Adoption ramp-up period before final checkpoint | Phase 5 | 2027-04-08 | 2027-06-30 | 60 | 5.4b
5.4c | Final adoption checkpoint (60 percent target) | Phase 5 | 2027-07-01 | 2027-07-02 | 2 | 5.wait3
6.1 | Data preparation and cleaning | Phase 6 | 2027-02-04 | 2027-02-08 | 3 | 4.2c
6.2a | Training of churn prediction model | Phase 6 | 2027-02-09 | 2027-02-18 | 8 | 6.1
6.2b | Validation and performance testing | Phase 6 | 2027-02-19 | 2027-02-24 | 4 | 6.2a
6.3 | Integration into dashboard | Phase 6 | 2027-02-25 | 2027-03-03 | 5 | 6.2b
7.1 | Full system testing across pilot stores | Phase 7 | 2027-07-05 | 2027-07-09 | 5 | 5.4c,6.3
7.2a | Feedback from checkout staff | Phase 7 | 2027-07-12 | 2027-07-15 | 4 | 7.1
7.2b | Feedback from customers | Phase 7 | 2027-07-12 | 2027-07-16 | 5 | 7.1
7.2c | Synthesis and analysis of feedback | Phase 7 | 2027-07-19 | 2027-07-21 | 3 | 7.2a,7.2b
7.3 | Final measurement of regular customer rate | Phase 7 | 2027-07-22 | 2027-07-26 | 3 | 7.2c
7.4 | Preparation of pilot assessment report | Phase 7 | 2027-07-27 | 2027-07-30 | 4 | 7.3
LEGEND
Phase 2 |  | Consent, legal & POS integration
Phase 3 |  | Communication & training preparation
Phase 4 |  | Data logging & validation
Phase 5 |  | Pilot rollout & adoption campaign
Phase 6 |  | Analytics & churn model
Phase 7 |  | Full testing, feedback & assessment
Waiting period |  | Deliberate waiting / data accumulation period