## Project Schedule
Activity ID | Activity Name | Duration (days) | Start Date | Finish Date | Dependencies | Assigned Resource | Project Start Date | 2026-09-01
2.0 | Design and legal validation of consent mechanism and privacy notice | 11 | 2026-09-01 | 2026-09-15 | - | Legal Consultant
2.1a | Decision on identification method | 1 | 2026-09-01 | 2026-09-01 | - | Developer / Technical Lead
2.1b | Visual design of the chosen system | 5 | 2026-09-02 | 2026-09-08 | 2.1a | UI/UX Designer |  |  | 2.1a
2.2a | Technical audit of POS terminal | 3 | 2026-09-01 | 2026-09-03 | - | Developer / Technical Lead
2.2a-bis | Deep technical exploration of POS API | 12 | 2026-09-04 | 2026-09-21 | 2.2a | Developer / Technical Lead |  |  | 2.2a
2.2b | Development of POS integration connector | 10 | 2026-09-22 | 2026-10-05 | 2.2a-bis | Developer / Technical Lead |  |  | 2.2a-bis
2.2c | Testing of invoice to card linkage | 5 | 2026-10-06 | 2026-10-12 | 2.2b | QA Tester |  |  | 2.2b
2.3a | Dashboard mockup and data architecture design | 4 | 2026-10-06 | 2026-10-09 | 2.2b | UI/UX Designer |  |  | 2.2b
2.3b | Development of dashboard interface and data connection | 8 | 2026-10-12 | 2026-10-21 | 2.3a | Developer / Technical Lead |  |  | 2.3a
2.4 | Internal testing before pilot deployment | 7 | 2026-10-22 | 2026-10-30 | 2.2c,2.3b,2.1b | QA Tester |  |  | 2.2c | 2.3b | 2.1b
3.1a | Basic analysis of purchase patterns | 4 | 2026-09-01 | 2026-09-04 | - | Business Analyst
3.1b | Definition of incentive mechanism | 2 | 2026-09-07 | 2026-09-08 | 3.1a | Marketing Coordinator |  |  | 3.1a
3.2a | Design of communication materials | 2 | 2026-09-09 | 2026-09-10 | 3.1b | Graphic Designer |  |  | 3.1b
3.2b | Review and validation cycle | 2 | 2026-09-11 | 2026-09-14 | 3.2a | Marketing Coordinator |  |  | 3.2a
3.2c | Printing and installation | 5 | 2026-09-15 | 2026-09-21 | 3.2b | External Printing Service |  |  | 3.2b
3.3 | Development of training script for checkout staff | 3 | 2026-09-09 | 2026-09-11 | 3.1b | Marketing Coordinator |  |  | 3.1b
4.1 | Activation of data logging | 2 | 2026-11-02 | 2026-11-03 | 2.4 | Data Analyst |  |  | 2.4
4.wait1 | Data accumulation period before first checkpoint | 20 | 2026-11-04 | 2026-12-01 | 4.1 | - |  |  | 4.1
4.2a | First data quality checkpoint | 2 | 2026-12-02 | 2026-12-03 | 4.wait1 | Data Analyst |  |  | 4.wait1
4.wait2 | Data accumulation period before second checkpoint | 20 | 2026-12-04 | 2026-12-31 | 4.2a | - |  |  | 4.2a
4.2b | Second data quality checkpoint | 2 | 2027-01-01 | 2027-01-04 | 4.wait2 | Data Analyst |  |  | 4.wait2
4.wait3 | Data accumulation period before final validation | 20 | 2027-01-05 | 2027-02-01 | 4.2b | - |  |  | 4.2b
4.2c | Final data quality validation (3 months of data) | 2 | 2027-02-02 | 2027-02-03 | 4.wait3 | Data Analyst |  |  | 4.wait3
5.1 | Distribution of loyalty cards | 3 | 2026-11-02 | 2026-11-04 | 2.4,3.2c,2.0 | Checkout Staff |  |  | 2.4 | 3.2c | 2.0
5.2 | Training delivery and observation tour | 4 | 2026-11-05 | 2026-11-10 | 3.3,5.1 | Marketing Coordinator |  |  | 3.3 | 5.1
5.3 | Launch of discount voucher campaign | 2 | 2026-11-11 | 2026-11-12 | 5.2 | Marketing Coordinator |  |  | 5.2
5.wait1 | Adoption ramp-up period before first checkpoint | 40 | 2026-11-13 | 2027-01-07 | 5.3 | - |  |  | 5.3
5.4a | First adoption checkpoint | 2 | 2027-01-08 | 2027-01-11 | 5.wait1 | Marketing Coordinator |  |  | 5.wait1
5.wait2 | Adoption ramp-up period before mid checkpoint | 60 | 2027-01-12 | 2027-04-05 | 5.4a | - |  |  | 5.4a
5.4b | Mid campaign adoption checkpoint | 2 | 2027-04-06 | 2027-04-07 | 5.wait2 | Marketing Coordinator |  |  | 5.wait2
5.wait3 | Adoption ramp-up period before final checkpoint | 60 | 2027-04-08 | 2027-06-30 | 5.4b | - |  |  | 5.4b
5.4c | Final adoption checkpoint (60 percent target) | 2 | 2027-07-01 | 2027-07-02 | 5.wait3 | Marketing Coordinator |  |  | 5.wait3
6.1 | Data preparation and cleaning | 3 | 2027-02-04 | 2027-02-08 | 4.2c | Data Scientist |  |  | 4.2c
6.2a | Training of churn prediction model | 8 | 2027-02-09 | 2027-02-18 | 6.1 | Data Scientist |  |  | 6.1
6.2b | Validation and performance testing | 4 | 2027-02-19 | 2027-02-24 | 6.2a | Data Scientist |  |  | 6.2a
6.3 | Integration into dashboard | 5 | 2027-02-25 | 2027-03-03 | 6.2b | Developer / Technical Lead |  |  | 6.2b
7.1 | Full system testing across pilot stores | 5 | 2027-07-05 | 2027-07-09 | 5.4c,6.3 | QA Tester |  |  | 5.4c | 6.3
7.2a | Feedback from checkout staff | 4 | 2027-07-12 | 2027-07-15 | 7.1 | Business Analyst |  |  | 7.1
7.2b | Feedback from customers | 5 | 2027-07-12 | 2027-07-16 | 7.1 | Business Analyst |  |  | 7.1
7.2c | Synthesis and analysis of feedback | 3 | 2027-07-19 | 2027-07-21 | 7.2a,7.2b | Business Analyst |  |  | 7.2a | 7.2b
7.3 | Final measurement of regular customer rate | 3 | 2027-07-22 | 2027-07-26 | 7.2c | Project Manager |  |  | 7.2c
7.4 | Preparation of pilot assessment report | 4 | 2027-07-27 | 2027-07-30 | 7.3 | Project Manager |  |  | 7.3
Formulas:
Finish Date = WORKDAY([Start Date],[Duration (days)]-1)